## Product Catalog
Project Name | FoodBox
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Yashwanth
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
For an application to launch,the highest busiiness value will be when the user is able to use the application in a flexible way. | US001 | Admin can change the password. | as an administrator, I want to have have an option to change the password because of the security concerns. | New
| US002 | manage all the food items. | as an administrator, I want to have an option to view the list of all the food items users and products by id or all of them at once and also able to search them . | New
| US003 | categorize the food items and sorting them out. | as an administrator, I want to have an option delete the list offood items that are not avialable etc | New
| US004 | map the food items to users and report them by date and category. | as an administartor, I want to have an option to map the purchased food items to the users and report them by date and category. | New
| US005 | able to look at the payment details | as an administrator,I want to have an option to view the payment details of the user and view them by data and category. | New

## Sprint Planning
Project Name | FoodBox
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Yashwanth
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
For an application to launch,the highest busiiness value will be when the user is able to use the application in a flexible way. | US001 | Admin can change the password. | as an administrator, I want to have have an option to change the password because of the security concerns. | 5 | 1
| US002 | manage all the food items. | as an administrator, I want to have an option to view the list of all the food items users and products by id or all of them at once and also able to search them . | 5 | 1
| US003 | categorize the food items and sorting them out. | as an administrator, I want to have an option delete the list offood items that are not avialable etc | 5 | 2
| US004 | map the food items to users and report them by date and category. | as an administartor, I want to have an option to map the purchased food items to the users and report them by date and category. | 5 | 3
| US005 | able to look at the payment details | as an administrator,I want to have an option to view the payment details of the user and view them by data and category. | 8 | 4